## Sheet1
Task Name | Start Time | Duration(week)
Find additional data sets | 2016-10-05 | 7
Synchronize data sets format | 2016-10-12 | 7
Prepare text description | 2016-10-12 | 7
Data cleaning | 2016-10-19 | 10
Documente data cleaning process | 2016-10-29 | 4
Meet professor | 2016-10-26 | 7
Work on the feedback | 2016-11-02 | 4
R scripts | 2016-11-02 | 14
R plot | 2016-11-16 | 7
Presentation | 2016-11-23 | 14
Extra credit | 2016-11-30 | 7
Git packages | 2016-11-30 | 7